## All Requirements
ClinEdOps — Master Requirements Tracker
NUH Medical Affairs (Education) — IMDA Open Innovation Challenge Call 28 ¦ Prepared by SlashLLM ¦ April 2026
Req ID | Module / Area | Category | Requirement | Description | Priority | Source | Acceptance Criteria | Status | Assigned To | Sprint | Notes
FR-STU-001 | Student & Tutor Lifecycle | Functional | Student profile creation | Create student records with fields: full name, student code, institution, discipline, programme, cohort, academic cycle, posting status | P0 | CB, PRD | Student record created with all mandatory fields validated; appears in student list
FR-STU-002 | Student & Tutor Lifecycle | Functional | Student status lifecycle tracking | Track student status: Pending Onboard → Active → Completed → Offboarded. Status transitions auditable | P0 | CB, PRD | Status changes reflected in real-time; each transition logged in audit trail
FR-STU-003 | Student & Tutor Lifecycle | Functional | Assign students to postings | Assign students to departments, postings, tutors, and academic cycles with date ranges | P0 | CB, PRD | Student linked to posting with start/end dates; visible on student profile and posting detail
FR-STU-004 | Student & Tutor Lifecycle | Functional | Student detail view | View student profile card with posting history timeline, feedback received, teaching hours, and audit trail | P0 | PRD | All associated data rendered on single profile page with timeline view
FR-STU-005 | Student & Tutor Lifecycle | Functional | Student list with filters | Filterable student list by discipline, institution, status, academic cycle. Sortable table with bulk actions and export | P0 | PRD | Filters reduce results correctly; sort toggles work; CSV/Excel export produces valid file
FR-STU-006 | Student & Tutor Lifecycle | Functional | Single student creation form | Add individual student via form with field-level validation (required fields, format checks, duplicate detection) | P0 | PRD | Form validates all required fields; duplicate student code rejected with error message
FR-STU-007 | Student & Tutor Lifecycle | Functional | Student record editing | Update existing student records (programme admin and above) | P0 | PRD | Edits saved successfully; changes logged in audit trail with before/after values
FR-STU-008 | Student & Tutor Lifecycle | Functional | Student soft delete | Deactivate student records (super admin only) without hard deletion. Soft-deleted records retained for historical/audit | P1 | PRD | Student marked inactive; excluded from active lists; data retained in database
FR-STU-009 | Student & Tutor Lifecycle | Functional | Student offboarding workflow | Offline offboarding process capturing final data, posting completion status, and feedback closure | P1 | PRD | Offboarding checklist completed; student status moves to Offboarded; final data captured
FR-STU-010 | Student & Tutor Lifecycle | Functional | Historical student record retention | Retain completed/offboarded student records indefinitely for accreditation and audit | P1 | PRD | Historical records accessible via search/filter; no data loss after academic cycle closure
FR-TUT-001 | Student & Tutor Lifecycle | Functional | Tutor profile creation | Create tutor records with: full name, staff code, department, specialty, discipline, billable rate (SGD), status | P0 | CB, PRD | Tutor record created; billable rate stored as NUMERIC(10,2); appears in tutor list
FR-TUT-002 | Student & Tutor Lifecycle | Functional | Tutor detail view | View tutor profile with teaching hours by cycle, feedback summary, billing summary, and assigned students | P0 | PRD | All associated data rendered; hours aggregated correctly by cycle
FR-TUT-003 | Student & Tutor Lifecycle | Functional | Tutor list with filters | Filterable, sortable tutor list showing current teaching load and status badges | P0 | PRD | Filters work correctly; teaching load calculated from approved hours
FR-TUT-004 | Student & Tutor Lifecycle | Functional | Tutor record editing | Update tutor records including billable rate changes (admin only) | P0 | PRD | Edits saved; billable rate changes logged in audit trail
FR-TUT-005 | Student & Tutor Lifecycle | Functional | Tutor billing data export | Export billing-ready hours data per tutor with approved hours mapped to billable rates | P1 | CB, PRD | Export produces accurate billing summary with hours × rate calculations
FR-TUT-006 | Student & Tutor Lifecycle | Functional | Tutor active/inactive toggle | Deactivate tutors who are no longer teaching without deleting historical data | P1 | PRD | Inactive tutors hidden from assignment dropdowns; historical data preserved
FR-PST-001 | Postings Management | Functional | Create posting | Create postings with: student assignment, department, academic cycle, start/end date, primary tutor, status | P0 | PRD | Posting created with all fields; appears on calendar and table views
FR-PST-002 | Postings Management | Functional | Posting status lifecycle | Track posting status: Scheduled → Active → Completed → Cancelled | P0 | PRD | Status transitions enforced; automated status change on start/end dates
FR-PST-003 | Postings Management | Functional | Assign multiple tutors to posting | Link multiple tutors to a single posting via junction table with role labels (primary, ad hoc) | P0 | PRD | Multiple tutors assigned; roles visible on posting detail page
FR-PST-004 | Postings Management | Functional | Posting list views | Display postings in calendar and table view; filter by department, discipline, date range, status | P0 | PRD | Both views render correctly; filters reduce results accurately
FR-PST-005 | Postings Management | Functional | Posting detail view | View posting with: student info, assigned tutors, teaching sessions, survey status, timeline | P0 | PRD | All related data displayed; survey completion status visible
FR-PST-006 | Postings Management | Functional | Edit posting | Update posting dates, tutor assignments, department (admin only) | P0 | PRD | Changes saved; audit trail captures before/after; linked sessions unaffected
FR-TH-001 | Teaching Hours Tracking | Functional | Log teaching session | Tutors log sessions with: date, time, duration, session type, linked students, department, description | P0 | CB, PRD | Session created with all fields; duration stored as INTEGER minutes
FR-TH-002 | Teaching Hours Tracking | Functional | Bulk session creation | Create multiple recurring scheduled sessions in one action | P0 | PRD | Multiple sessions created matching recurrence pattern; each individually editable
FR-TH-003 | Teaching Hours Tracking | Functional | Save session as draft | Tutors can save incomplete session entries as drafts before submission | P0 | PRD | Draft saved; retrievable from My Sessions list; editable before submission
FR-TH-004 | Teaching Hours Tracking | Functional | Submit session for approval | Tutor submits session entry, changing status from draft to submitted | P0 | PRD | Status changes to submitted; notification sent to supervisor
FR-TH-005 | Teaching Hours Tracking | Functional | Multi-level approval workflow | Approval chain: Tutor submits → Supervisor reviews → Admin approves | P0 | CB, PRD | Status progresses through workflow; each approval logged with approver ID and timestamp
FR-TH-006 | Teaching Hours Tracking | Functional | Reject session with reason | Supervisor or admin can reject a submitted session with mandatory reason text | P0 | PRD | Status changes to rejected; reason stored; tutor notified with reason
FR-TH-007 | Teaching Hours Tracking | Functional | Flag session as anomalous | Admin can flag sessions for review (duplicate detection, high hours, outside posting period) | P0 | CB, PRD | Flagged sessions visually distinguished; appear in flagged items dashboard
FR-TH-008 | Teaching Hours Tracking | Functional | Automated anomaly detection | Auto-flag: duplicate sessions, unusually high hours (configurable threshold), sessions outside posting period | P0 | CB, PRD | Auto-flags triggered correctly based on rules; flagged sessions require manual review
FR-TH-009 | Teaching Hours Tracking | Functional | Student-side hour confirmation | Students can optionally view and confirm their attendance at logged sessions | P1 | PRD | Student confirmation status visible on session detail; optional — not blocking
FR-TH-010 | Teaching Hours Tracking | Functional | Map hours to billable rates | Approved hours automatically mapped to tutor's billable rate for compensation calculation | P1 | CB, PRD | Billable hours = approved minutes ÷ 60 × billable rate; calculation verified
FR-TH-011 | Teaching Hours Tracking | Functional | Teaching hours dashboard | Real-time dashboard showing approved, pending, and flagged hours by tutor, department, discipline | P0 | CB, PRD | Dashboard data matches database aggregations; filters work correctly
FR-TH-012 | Teaching Hours Tracking | Functional | My Sessions view (Tutor) | Personal list of sessions with status tags and hours summary | P0 | PRD | Tutor sees only own sessions; totals match sum of individual sessions
FR-TH-013 | Teaching Hours Tracking | Functional | Sessions admin view | All sessions across tutors; filter by status, department, tutor; bulk approve; anomaly badges | P0 | PRD | Admin sees all sessions; bulk approve changes status for selected items
FR-TH-014 | Teaching Hours Tracking | Functional | Session detail view | Full session info with approval history, student list, and audit trail | P0 | PRD | Complete history displayed; audit trail shows all status changes
FR-TH-015 | Teaching Hours Tracking | Functional | Teaching hours bar charts | Bar charts showing hours by tutor/department; filterable by date/discipline; exportable | P0 | PRD | Charts render correctly; data matches underlying records; export produces image/PDF
FR-TH-016 | Teaching Hours Tracking | Functional | Export teaching hours summary | Export hours summary for billing and payroll in Excel/CSV format | P1 | CB, PRD | Export contains all approved hours with tutor, department, dates, billable amounts
FR-SV-001 | Survey & Feedback Engine | Functional | Survey template builder | Create survey templates configurable by discipline, posting type, semester, or academic cycle | P0 | CB, PRD | Template created with all configuration options; saved and retrievable
FR-SV-002 | Survey & Feedback Engine | Functional | Question types support | Support question types: rating (Likert scale), free text, and multi-choice | P0 | PRD | All three question types render correctly; responses captured accurately
FR-SV-003 | Survey & Feedback Engine | Functional | 5-point Likert scoring matrix | Standard scoring matrix based out of 5 as required by challenge brief | P0 | CB | Rating questions display 1–5 scale; scores stored correctly
FR-SV-004 | Survey & Feedback Engine | Functional | Drag-and-drop question builder | Drag-and-drop interface for ordering and managing questions within templates | P1 | PRD | Questions reorderable via drag; order persisted on save
FR-SV-005 | Survey & Feedback Engine | Functional | Low-score threshold configuration | Set configurable threshold (default < 3/5) below which compulsory text comment is required | P0 | CB, PRD | Text field appears when rating ≤ threshold; submission blocked if text field empty
FR-SV-006 | Survey & Feedback Engine | Functional | Low-score auto-flagging | Auto-flag low-score submissions to programme admin and supervisor for follow-up | P0 | CB, PRD | Flagged submissions appear in admin dashboard; notification sent to relevant users
FR-SV-007 | Survey & Feedback Engine | Functional | Batched/consolidated surveys | Group multiple tutor interactions into a single daily/weekly survey per student | P0 | CB, PRD | Student receives one consolidated survey covering all interactions in the batch period
FR-SV-008 | Survey & Feedback Engine | Functional | Configurable survey cadence | Support per-posting, midpoint check-in, and end-of-posting survey dispatch schedules | P0 | CB, PRD | Surveys dispatched at configured cadence; correct students and tutors linked
FR-SV-009 | Survey & Feedback Engine | Functional | Midpoint feedback form | Structured qualitative check-in form dispatched at posting midpoint | P1 | PRD | Midpoint survey dispatched halfway through posting period; distinct from end-of-posting
FR-SV-010 | Survey & Feedback Engine | Functional | Automated survey reminders | Configurable reminder intervals for incomplete survey submissions | P0 | CB, PRD | Reminders sent at configured intervals; stop after submission; escalation after threshold
FR-SV-011 | Survey & Feedback Engine | Functional | Survey submission by student | Form with progress bar, Likert scale ratings, conditional text fields, submit confirmation | P0 | PRD | Student completes and submits; responses stored with timestamp
FR-SV-012 | Survey & Feedback Engine | Functional | Pending surveys view (Student) | Student sees list of pending surveys with due dates and progress indicator | P0 | PRD | Only pending/incomplete surveys shown; progress accurate; one-click to start
FR-SV-013 | Survey & Feedback Engine | Functional | Real-time submission rate monitoring | Monitor submission rates by cohort, posting, and discipline in real-time | P0 | CB, PRD | Dashboard shows completion percentages; updates as submissions arrive
FR-SV-014 | Survey & Feedback Engine | Functional | Positive/negative feedback categorisation | Tools to filter and categorise feedback as positive or negative | P1 | CB, PRD | Feedback tagged by sentiment; filterable in admin view
FR-SV-015 | Survey & Feedback Engine | Functional | Feedback admin view | Completion rate progress bars, flagged submissions list, feedback comment browser with sentiment filter | P0 | PRD | Admin sees all feedback data; filters work; flagged items highlighted
FR-SV-016 | Survey & Feedback Engine | Functional | Feedback summary (Tutor) | Personal view of aggregated scores, comment excerpts, and trend over time | P0 | PRD | Tutor sees own feedback only; scores aggregated correctly; trend chart renders
FR-SV-017 | Survey & Feedback Engine | Functional | Customisable feedback reports | Generate customisable reports for supervisors, tutors, institutions for awards or appraisal | P1 | CB | Reports filterable by tutor/institution/period; exportable to PDF/Excel
FR-SV-018 | Survey & Feedback Engine | Functional | Survey template clone/deactivate | Clone existing templates; deactivate templates no longer in use | P1 | PRD | Cloned template is independent copy; deactivated template hidden from dispatch
FR-RPT-001 | Reporting & Analytics | Functional | Role-specific dashboards | Different dashboard views for Admin, HOD, Tutor, Student with role-appropriate data | P0 | CB, PRD | Each role sees appropriate dashboard; data scoped to role permissions
FR-RPT-002 | Reporting & Analytics | Functional | Dashboard drill-down | Click any aggregate metric to see individual-level detail | P0 | PRD | Clicking KPI navigates to filtered detail view; data matches aggregate
FR-RPT-003 | Reporting & Analytics | Functional | Faculty Appraisal report | Pre-built report aggregating teaching hours, feedback scores, student outcomes per tutor | P0 | CB, PRD | Report generates correctly; data verified against source records
FR-RPT-004 | Reporting & Analytics | Functional | Tutor Billing report | Pre-built report with approved hours × billable rates per tutor for compensation | P0 | CB, PRD | Billing totals match approved hours × rates; exportable to Excel
FR-RPT-005 | Reporting & Analytics | Functional | Teaching Award Nominations report | Report surfacing tutors with high positive feedback for award consideration | P1 | CB, PRD | Report filters by positive feedback threshold; includes supporting data
FR-RPT-006 | Reporting & Analytics | Functional | Programme Quality Review report | Report covering feedback trends, completion rates, quality indicators across programmes | P1 | PRD | Report spans multiple programmes; comparative data accurate
FR-RPT-007 | Reporting & Analytics | Functional | Accreditation report | Report summarising compliance data, teaching hours, feedback for accreditation review | P1 | CB, PRD | Report meets accreditation data requirements; exportable
FR-RPT-008 | Reporting & Analytics | Functional | Custom report builder | Admin selects fields, applies filters, previews results, generates and downloads | P1 | PRD | Builder produces correct results; preview matches final export
FR-RPT-009 | Reporting & Analytics | Functional | Report export formats | Export reports in PDF, Excel (.xlsx), and CSV formats | P0 | CB, PRD | All three formats produce valid, readable files with correct data
FR-RPT-010 | Reporting & Analytics | Functional | Scheduled report delivery | Auto-generate and email reports on configurable schedule | P1 | PRD | Reports generated and emailed on schedule; recipients receive correct reports
FR-RPT-011 | Reporting & Analytics | Functional | Comparative analytics | Semester-on-semester, year-on-year teaching quality trend analysis | P2 | PRD | Trend charts show data across multiple periods; comparison calculations correct
FR-RPT-012 | Reporting & Analytics | Functional | Reports Centre | List of available report templates with generate + download buttons and recent exports | P0 | PRD | All report types listed; generation triggers async job; download available
FR-RPT-013 | Reporting & Analytics | Functional | Report generation target < 1 minute | All pre-built reports generate end-to-end in under 60 seconds | P0 | CB | P95 report generation < 60 seconds
FR-NTF-001 | Notifications & Alerts | Functional | In-app notification centre | Full notification list with filter, mark all read, click-through to relevant record | P0 | CB, PRD | Notifications render correctly; click navigates to source record
FR-NTF-002 | Notifications & Alerts | Functional | Email notifications (configurable) | Email alerts for: pending feedback, approval required, low scores flagged, deadlines | P1 | CB, PRD | Emails sent via AWS SES; content accurate; configurable per user preference
FR-NTF-003 | Notifications & Alerts | Functional | Push reminders for surveys | Reminder notifications for students with incomplete survey submissions | P0 | CB, PRD | Reminders delivered at configured intervals; cease after submission
FR-NTF-004 | Notifications & Alerts | Functional | Escalation alerts | If feedback overdue past threshold, escalate notification to supervisor | P1 | PRD | Escalation triggered after threshold; supervisor receives notification
FR-NTF-005 | Notifications & Alerts | Functional | Admin broadcast | Send announcements to student or tutor groups | P1 | PRD | Broadcast reaches all members of selected group
FR-NTF-006 | Notifications & Alerts | Functional | Notification badge count | Header bar shows unread notification count badge | P0 | PRD | Badge count matches unread notifications; updates in real-time
FR-RBAC-001 | Role-Based Access Control | Functional | Five core roles | System supports: Super Admin, Programme Admin, Supervisor, Tutor/Clinician, Student | P0 | CB, PRD | All five roles creatable; each has distinct default permissions
FR-RBAC-002 | Role-Based Access Control | Functional | Customisable permission sets | Super admin can modify default permissions per role | P1 | CB, PRD | Permissions editable via RBAC Configuration screen; changes effective immediately
FR-RBAC-003 | Role-Based Access Control | Functional | Approval hierarchy configuration | Define who approves what within each workflow | P1 | CB, PRD | Approval chains configurable; workflow respects configured hierarchy
FR-RBAC-004 | Role-Based Access Control | Functional | Discipline-scoped access | Programme admins see only their assigned discipline by default | P0 | CB, PRD | Data filtered by discipline; admin cannot access other discipline data
FR-RBAC-005 | Role-Based Access Control | Functional | Cross-discipline view | Department heads and above see data across all disciplines | P0 | PRD | HOD and Super Admin see all disciplines
FR-RBAC-006 | Role-Based Access Control | Functional | Time-limited guest access | Temporary access for visiting educators or external accreditors with expiry | P2 | PRD | Guest account created with expiry; access revoked automatically after expiry
FR-RBAC-007 | Role-Based Access Control | Functional | Role-based navigation | Sidebar menu items shown/hidden based on authenticated user role | P0 | PRD | Each role sees only permitted menu items; direct URL access blocked
FR-RBAC-008 | Role-Based Access Control | Functional | RBAC permission matrix editor | Visual editor for super admin to view and modify role-permission matrix | P1 | PRD | Matrix displays all roles × permissions; toggles work; changes persist
FR-AUD-001 | Audit Trail | Functional | Immutable audit log | Log all create, update, delete, approve actions with actor, action type, timestamp, affected record, before/after | P0 | CB, PRD | Every data mutation creates audit entry; entries cannot be modified/deleted
FR-AUD-002 | Audit Trail | Functional | Filterable audit log viewer | Admin can search and filter audit log by actor, action type, resource type, date range | P0 | PRD | Filters reduce results correctly; search returns matching entries
FR-AUD-003 | Audit Trail | Functional | Exportable audit log | Export audit log for compliance, PDPA audit, or accreditation review | P1 | CB, PRD | Export produces complete, accurate audit data in CSV/Excel
FR-AUD-004 | Audit Trail | Functional | Configurable retention policy | Audit log retention configurable; default 7 years per PDPA requirements | P1 | PRD | Retention policy enforced; data older than policy auto-archived or purged
FR-AUD-005 | Audit Trail | Functional | IP address capture | Capture client IP address for each audit log entry | P1 | PRD | IP address stored with each entry; available in exported logs
FR-IMP-001 | Batch Import / Data Mgmt | Functional | Excel and CSV import | Upload Excel and CSV files for student and tutor batch creation | P0 | CB, PRD | Both file formats accepted; data parsed correctly
FR-IMP-002 | Batch Import / Data Mgmt | Functional | Field mapping interface | Map import file columns to ClinEdOps system fields via drag-drop or dropdown | P0 | PRD | All system fields available for mapping; unmapped columns skipped
FR-IMP-003 | Batch Import / Data Mgmt | Functional | Pre-import validation | Check duplicates, missing required fields, format errors before committing | P0 | CB, PRD | Validation report shows all errors; user can review before proceeding
FR-IMP-004 | Batch Import / Data Mgmt | Functional | Import preview with error highlighting | Preview table with row-level error highlighting (red = errors, yellow = warnings) | P0 | PRD | Errors visually highlighted; user can correct or skip problematic rows
FR-IMP-005 | Batch Import / Data Mgmt | Functional | Import history log | Track who imported what, when, file name, record count, error count | P1 | PRD | History shows all past imports with metadata
FR-IMP-006 | Batch Import / Data Mgmt | Functional | FormSG webhook ingestion | Accept FormSG form submission data via webhook for real-time data ingestion | P2 | PRD | Webhook endpoint receives and processes FormSG payloads
FR-IMP-007 | Batch Import / Data Mgmt | Functional | Duplicate detection on import | Detect and flag duplicate records based on student/staff code during import | P0 | CB, PRD | Duplicates flagged in preview; user can choose to skip or update
FR-AUTH-001 | Authentication & Security | Functional | Email + password login | Login with email and password; returns access + refresh tokens | P0 | PRD | Valid credentials return tokens; invalid show error message
FR-AUTH-002 | Authentication & Security | Functional | JWT RS256 authentication | Asymmetric JWT signing with RS256; private key in AWS Secrets Manager | P0 | PRD | Tokens verified with public key; tampered tokens rejected
FR-AUTH-003 | Authentication & Security | Functional | Access token (15-min TTL) | Short-lived access tokens stored in memory (not localStorage) | P0 | PRD | Token expires after 15 minutes; refresh flow triggered automatically
FR-AUTH-004 | Authentication & Security | Functional | Refresh token (7-day TTL) | HTTP-only secure cookie; server-side rotation on use | P0 | PRD | Refresh produces new access token; old refresh token invalidated
FR-AUTH-005 | Authentication & Security | Functional | Forgot password flow | Send password reset email with time-limited token | P1 | PRD | Email sent within 30 seconds; reset link expires after configured time
FR-AUTH-006 | Authentication & Security | Functional | First login onboarding | Forced password change + profile completion on first login | P1 | PRD | New users must change password and complete profile before access
FR-AUTH-007 | Authentication & Security | Functional | User management (Super Admin) | List all users; create/edit/deactivate accounts; assign roles | P0 | PRD | CRUD operations work; role changes effective immediately
FR-AUTH-008 | Authentication & Security | Functional | Session logout | Invalidate refresh token on logout | P0 | PRD | Logout clears tokens; subsequent API calls rejected
FR-AUTH-009 | Authentication & Security | Functional | Access logs | Log all login attempts (success/failure) with timestamps | P1 | CB | Login events recorded; viewable in audit log
FR-ACY-001 | Academic Cycle & Department | Functional | Academic cycle management | Create/manage academic cycles with start date, end date, active status | P0 | PRD | Cycles created with date ranges; only one cycle active per discipline
FR-ACY-002 | Academic Cycle & Department | Functional | Activate/close cycles | Admin can activate and close cycles; closing triggers end-of-cycle workflows | P0 | PRD | Activation/closure enforced; downstream data respects cycle boundaries
FR-ACY-003 | Academic Cycle & Department | Functional | Department management | Add/edit departments with: name, division, discipline, head | P0 | PRD | Departments created; head assigned; department available in posting creation
FR-ACY-004 | Academic Cycle & Department | Functional | Assign department heads | Link department heads to departments for cross-discipline oversight | P1 | PRD | Department head sees their department data in dashboard
FR-INT-001 | System Integrations | Functional | NUHS Jobplan Portal integration | Sync tutor schedules and job plan hours via REST API / DB sync | P2 | CB, PRD | Tutor schedule data flows into ClinEdOps; data matches source
FR-INT-002 | System Integrations | Functional | NUS BLUE System integration | Import student records, academic calendar, posting schedules via REST API | P2 | CB, PRD | Student data imported; calendar events synced; no duplicates
FR-INT-003 | System Integrations | Functional | Teaching Activities System (TAS) integration | Bi-directional sync of teaching activity data via REST API / CSV | P2 | CB, PRD | Data flows both directions; conflict resolution handled
FR-INT-004 | System Integrations | Functional | FormSG data ingestion | Import student/tutor data from FormSG via webhook or CSV export | P2 | CB, PRD | FormSG submissions appear in ClinEdOps; data mapped correctly
FR-INT-005 | System Integrations | Functional | AWS SES email integration | Transactional email delivery for notifications, reminders, report distribution | P1 | PRD | Emails delivered via SES; SPF/DKIM/DMARC authenticated
FR-INT-006 | System Integrations | Functional | AWS S3 file storage | Store exports, attachments, audit logs in S3 with server-side encryption | P1 | PRD | Files stored in ap-southeast-1; SSE-S3 encryption; pre-signed URLs
FR-INT-007 | System Integrations | Functional | Integration status dashboard | Admin view showing connection status, sync logs, manual re-sync trigger | P2 | PRD | Status indicators; logs show last sync time and result
FR-UI-001 | UI / UX | Functional | Persistent left sidebar navigation | Collapsible sidebar with role-specific menu items | P0 | PRD | Sidebar renders with correct items per role; collapses/expands
FR-UI-002 | UI / UX | Functional | Top header bar | Breadcrumbs, notification bell with badge count, user avatar + dropdown menu | P0 | PRD | All elements render; bell shows count; dropdown has profile/logout
FR-UI-003 | UI / UX | Functional | Mobile-responsive layout | Sidebar collapses to bottom tab bar on mobile; full functionality ≥ 375px | P0 | CB, PRD | All features accessible on iPhone SE viewport; no horizontal scroll
FR-UI-004 | UI / UX | Functional | NUH branding on login | Login page with NUH branding, email/password fields, forgot password link | P0 | PRD | Login page renders with branding; all elements functional
FR-UI-005 | UI / UX | Functional | System settings page | Email configuration, notification defaults, PDPA data retention policy settings | P1 | PRD | Settings editable; changes take effect system-wide
NFR-PERF-001 | Performance | Non-Functional | API response time | P95 < 500ms for standard queries; < 2s for report generation triggers | P0 | PRD | Load test confirms P95 within threshold
NFR-PERF-002 | Performance | Non-Functional | Report generation time | < 60 seconds end-to-end for all pre-built report types | P0 | CB, PRD | Stopwatch timing confirms < 60s for each report type
NFR-PERF-003 | Performance | Non-Functional | Concurrent user support | Support 500+ concurrent users without degradation | P1 | PRD | Load test with 500 simulated users; no errors
NFR-PERF-004 | Performance | Non-Functional | Database query optimisation | Proper indexing; cursor-based pagination for large datasets | P1 | PRD | EXPLAIN ANALYZE confirms index usage; pagination consistent
NFR-PERF-005 | Performance | Non-Functional | Frontend bundle optimisation | Code splitting, lazy loading; initial load < 3s on 4G | P1 | PROP | Lighthouse score ≥ 80; LCP < 3s on throttled connection
NFR-REL-001 | Reliability & Availability | Non-Functional | Uptime SLA | 99.5% uptime during business hours (0800–2200 SGT) | P1 | PRD | Uptime monitoring confirms ≥ 99.5% over 30-day period
NFR-REL-002 | Reliability & Availability | Non-Functional | Database backups | Daily automated PostgreSQL backups; 30-day retention; PITR | P1 | PRD | Backup schedule verified; restoration tested successfully
NFR-REL-003 | Reliability & Availability | Non-Functional | Multi-AZ database deployment | RDS PostgreSQL in Multi-AZ for failover | P1 | PRD | Failover tested; application recovers within RDS failover SLA
NFR-REL-004 | Reliability & Availability | Non-Functional | Data integrity (transactions) | All multi-step writes wrapped in database transactions | P0 | PRD | Transaction rollback on failure; no partial writes
NFR-REL-005 | Reliability & Availability | Non-Functional | Error handling and recovery | Graceful error handling; no unhandled exceptions in production | P1 | PROP | Sentry captures all errors; user sees friendly error messages
NFR-SCL-001 | Scalability | Non-Functional | Horizontal auto-scaling | ECS Fargate auto-scaling: out at 70% CPU, in at 30% | P1 | PRD | Auto-scaling triggers tested; new containers within 2 minutes
NFR-SCL-002 | Scalability | Non-Functional | Database read replicas | RDS read replica for reporting queries | P2 | PRD | Reporting queries routed to read replica
NFR-SCL-003 | Scalability | Non-Functional | Redis caching | Cache dashboard aggregations and user sessions in Redis | P1 | PRD | Cache hit rate > 80%; invalidation on data changes
NFR-SCL-004 | Scalability | Non-Functional | Multi-tenant-ready architecture | Schema and RBAC designed to support multiple institutions post-POC | P2 | CB, PROP | Schema supports institution-level partitioning without migration
NFR-SCL-005 | Scalability | Non-Functional | Stateless API design | No server-side session state; any container can serve any request | P0 | PRD | Round-robin routing; no session affinity required
NFR-SEC-001 | Security | Non-Functional | HTTPS enforcement | TLS 1.2+ enforced on all endpoints; no HTTP access | P0 | PRD | All connections over HTTPS; HTTP redirects to HTTPS
NFR-SEC-002 | Security | Non-Functional | Password hashing | bcrypt with cost factor 12 for all password storage | P0 | PRD | Passwords verified as bcrypt hashed; plaintext never stored
NFR-SEC-003 | Security | Non-Functional | SQL injection prevention | All inputs validated with Pydantic; queries via SQLAlchemy ORM | P0 | PRD | Penetration test confirms no SQL injection vulnerabilities
NFR-SEC-004 | Security | Non-Functional | XSS protection | Input sanitisation; Content-Security-Policy headers | P0 | PRD | Penetration test confirms no XSS vulnerabilities
NFR-SEC-005 | Security | Non-Functional | AWS WAF | WAF rules on ALB for rate limiting, SQL injection, XSS protection | P1 | PRD | WAF rules active; malicious requests blocked
NFR-SEC-006 | Security | Non-Functional | Rate limiting | 1000 req/min per authenticated user; 100 req/min for public | P1 | PRD | Rate limits enforced; 429 on breach
NFR-SEC-007 | Security | Non-Functional | Secrets management | All secrets in AWS Secrets Manager; never in env vars or code | P1 | PRD | No secrets in codebase; Secrets Manager access verified
NFR-SEC-008 | Security | Non-Functional | S3 bucket security | Private bucket; SSE-S3 encryption; no public access; pre-signed URLs | P1 | PRD | Bucket policy blocks public access; pre-signed URLs expire
NFR-SEC-009 | Security | Non-Functional | Database encryption in transit | All DB connections via SSL/TLS; RDS in private subnet | P1 | PRD | Connection string uses SSL; RDS has no public endpoint
NFR-SEC-010 | Security | Non-Functional | Input validation | All API inputs validated server-side with Pydantic schemas | P0 | PRD | Invalid requests return 422 with validation error details
NFR-SEC-011 | Security | Non-Functional | Penetration testing | Third-party penetration test before production launch | P1 | PROP | Pentest completed; critical/high findings remediated
NFR-SEC-012 | Security | Non-Functional | Vulnerability scanning | Automated dependency and container image vulnerability scanning in CI/CD | P1 | PROP | Scanning on every PR; critical vulnerabilities block deployment
NFR-PDPA-001 | PDPA Compliance | Non-Functional | Data residency — Singapore | All data stored exclusively in AWS ap-southeast-1 | P0 | CB, PRD | All AWS resources in ap-southeast-1; no cross-region transfer
NFR-PDPA-002 | PDPA Compliance | Non-Functional | Access log retention | Access logs retained for 7 years (configurable) | P1 | PRD | Logs retained per policy; auto-archival working
NFR-PDPA-003 | PDPA Compliance | Non-Functional | Data export on request | Student/tutor data export available on request via admin | P1 | PRD | Admin can export individual's data in machine-readable format
NFR-PDPA-004 | PDPA Compliance | Non-Functional | Data deletion workflow | Soft delete for departed staff/students; configurable hard delete schedule | P1 | PRD | Soft delete removes from active views; hard delete runs on schedule
NFR-PDPA-005 | PDPA Compliance | Non-Functional | Privacy notice at first login | Privacy notice presented and acknowledged at first login | P1 | PRD | Notice displayed; acknowledgement logged
NFR-PDPA-006 | PDPA Compliance | Non-Functional | NUH as primary data owner | NUH retains ownership of all data; access controls enforce governance | P0 | CB | Platform confirms NUH as data owner
NFR-INF-001 | Infrastructure | Non-Functional | Docker containerisation | All services containerised; Docker Compose for dev; multi-stage builds | P0 | PRD | docker-compose up starts all services; images < 500MB
NFR-INF-002 | Infrastructure | Non-Functional | AWS ECS Fargate deployment | Production containers via ECS Fargate (serverless) | P1 | PRD | Services running on Fargate; health checks passing
NFR-INF-003 | Infrastructure | Non-Functional | CloudFront CDN | React SPA served via CloudFront for low-latency delivery | P1 | PRD | Cache hit ratio > 90%
NFR-INF-004 | Infrastructure | Non-Functional | Route 53 DNS | Custom domain configured via Route 53 | P1 | PRD | Domain resolves to CloudFront; SSL certificate valid
NFR-INF-005 | Infrastructure | Non-Functional | Infrastructure-as-Code | AWS CDK or Terraform for reproducible provisioning | P1 | PROP | IaC scripts provision full stack; reproducible
NFR-INF-006 | Infrastructure | Non-Functional | CI/CD pipeline | GitHub Actions for automated test, lint, build, deploy | P0 | PRD | Pipeline runs on PR; all checks pass before merge
NFR-INF-007 | Infrastructure | Non-Functional | Environment separation | Separate staging and production environments | P1 | PROP | Staging mirrors production; deployments tested in staging first
NFR-OBS-001 | Observability | Non-Functional | Application logging | Structured JSON logging; log levels (DEBUG, INFO, WARN, ERROR) | P1 | PROP | Logs queryable in CloudWatch; structured format
NFR-OBS-002 | Observability | Non-Functional | CloudWatch dashboards | Infrastructure metrics: CPU, memory, request count, error rate, latency | P1 | PROP | Dashboard shows real-time metrics; alarms configured
NFR-OBS-003 | Observability | Non-Functional | Sentry error tracking | Frontend and backend error tracking with Sentry SDK | P1 | PRD | Errors captured with stack traces; alerts on regression
NFR-OBS-004 | Observability | Non-Functional | Uptime monitoring | External uptime checks with alerting on downtime | P1 | PROP | Monitor checks every 1 minute; alert within 5 minutes
NFR-OBS-005 | Observability | Non-Functional | Operational runbooks / SOPs | Procedures for: incident response, deployment, backup, onboarding, admin | P1 | PROP | Runbooks cover all critical operations
NFR-ACC-001 | Accessibility | Non-Functional | WCAG 2.1 Level AA | Key user-facing screens comply with WCAG 2.1 AA | P1 | PRD | Automated accessibility audit passes on key screens
NFR-ACC-002 | Accessibility | Non-Functional | Browser support | Chrome 110+, Firefox 110+, Safari 16+, Edge 110+ | P0 | PRD | Core features functional on all supported browsers
NFR-ACC-003 | Accessibility | Non-Functional | Mobile responsive | Full functionality on viewport width ≥ 375px | P0 | PRD | All features accessible; touch targets ≥ 44px
NFR-ACC-004 | Accessibility | Non-Functional | Internationalisation-ready | English only for MVP; architecture supports i18n for future | P2 | PRD | All strings externalized; i18n framework integrated
NFR-TST-001 | Testing & Quality | Non-Functional | Backend unit tests | pytest coverage ≥ 80% on services/ and api/ | P0 | PRD | Coverage ≥ 80%; all tests pass
NFR-TST-002 | Testing & Quality | Non-Functional | Backend integration tests | API endpoint tests against test database | P0 | PRD | Integration tests pass with real database
NFR-TST-003 | Testing & Quality | Non-Functional | Auth tests | JWT generation/validation, role permission enforcement | P0 | PRD | All auth flows tested; unauthorized access rejected
NFR-TST-004 | Testing & Quality | Non-Functional | Async task tests | Celery task unit tests with mocked brokers | P1 | PRD | Task execution verified; email/report tested
NFR-TST-005 | Testing & Quality | Non-Functional | Frontend unit tests | Vitest + React Testing Library for components | P1 | PRD | Component tests pass; key interactions tested
NFR-TST-006 | Testing & Quality | Non-Functional | Frontend integration tests | Form submission flows, role-based rendering, navigation guards | P1 | PRD | Integration tests verify multi-component workflows
NFR-TST-007 | Testing & Quality | Non-Functional | End-to-end tests | Playwright or Cypress E2E: login, log session, submit survey, generate report | P1 | PRD | E2E tests pass on staging; cover critical journeys
NFR-TST-008 | Testing & Quality | Non-Functional | CI/CD test gates | All PRs: lint, type check, unit tests. Main: full suite | P0 | PRD | Failed checks block merge; zero failures for deploy
NFR-TST-009 | Testing & Quality | Non-Functional | Load testing | Simulate 500+ concurrent users; validate auto-scaling | P1 | PROP | Load test confirms NFR-PERF targets met
NFR-TST-010 | Testing & Quality | Non-Functional | User Acceptance Testing | UAT with NUH Medical Affairs staff across disciplines | P1 | PROP | UAT sign-off from NUH stakeholders
KPI-001 | Success Metrics | KPI | Manual data entry / tracking time | 50% reduction in manual data entry and tracking time | P0 | CB | Pre/post time-motion study comparing task duration
KPI-002 | Success Metrics | KPI | Data accuracy & completeness | ≥ 90% data accuracy and completeness | P0 | CB | Data quality audit on required fields across sample records
KPI-003 | Success Metrics | KPI | Report generation time | < 1 minute (80% reduction from ~5 min baseline) | P0 | CB | Stopwatch timing of report generation end-to-end
KPI-004 | Success Metrics | KPI | Survey completion rate | ≥ 30% increase in survey completion rate | P0 | CB | Compare completion rates before/after per cohort
KPI-005 | Success Metrics | KPI | Staff and user satisfaction | Measurable improvement in satisfaction | P1 | CB | Pre/post satisfaction survey of all user types
OOS-001 | Out of Scope | Out of Scope | Student grading / summative assessment | Not part of operational clinical education workflow | — | — | N/A
OOS-002 | Out of Scope | Out of Scope | Financial payment processing | Billing data export in scope; actual payment not | — | — | Phase B+
OOS-003 | Out of Scope | Out of Scope | Patient records / EHR / EMR integration | ClinEdOps is education operations, not clinical | — | — | N/A
OOS-004 | Out of Scope | Out of Scope | Native iOS / Android mobile app | Mobile-responsive web in scope; native app is future | — | — | Phase D
OOS-005 | Out of Scope | Out of Scope | Full multi-tenancy rollout | Single-tenant for POC; multi-tenant designed for future | — | — | Phase E
OOS-006 | Out of Scope | Out of Scope | Live video / teleconferencing | Not part of core operations workflow | — | — | N/A
OOS-007 | Out of Scope | Out of Scope | SSO (NUH Azure AD / Singpass) | Email/password for POC; SSO as production enhancement | — | — | Phase A
OOS-008 | Out of Scope | Out of Scope | AI/ML sentiment analysis | ML-ready pipeline designed; actual ML models post-production | — | — | Phase C

## Dashboard
Requirements Dashboard
Summary by Category
Category | Count | % of Total
Functional | 107 | 61.49%
Non-Functional | 54 | 31.03%
KPI | 5 | 2.874%
Out of Scope | 8 | 4.598%
TOTAL | 174 | 100%
Summary by Priority
Priority | Description | Count | % of In-Scope
P0 | Must-have for MVP/POC demo | 75 | 45.45%
P1 | Must-have for production launch | 70 | 42.42%
P2 | Should-have post-production | 15 | 9.091%
P3 | Nice-to-have future roadmap | 5 | 3.03%
TOTAL | In-scope requirements (excl. Out of Scope) | 165 | 100%
Requirements by Module
Module | Functional | Non-Functional | KPI | Out of Scope | Total
Student & Tutor Lifecycle | 16 | 0 | 0 | 0 | 16
Postings Management | 6 | 0 | 0 | 0 | 6
Teaching Hours Tracking | 16 | 0 | 0 | 0 | 16
Survey & Feedback Engine | 18 | 0 | 0 | 0 | 18
Reporting & Analytics | 13 | 0 | 0 | 0 | 13
Notifications & Alerts | 6 | 0 | 0 | 0 | 6
Role-Based Access Control | 8 | 0 | 0 | 0 | 8
Audit Trail | 5 | 0 | 0 | 0 | 5
Batch Import / Data Mgmt | 7 | 0 | 0 | 0 | 7
Authentication & Security | 9 | 0 | 0 | 0 | 9
Academic Cycle & Department | 4 | 0 | 0 | 0 | 4
System Integrations | 7 | 0 | 0 | 0 | 7
UI / UX | 5 | 0 | 0 | 0 | 5
Performance | 0 | 5 | 0 | 0 | 5
Reliability & Availability | 0 | 5 | 0 | 0 | 5
Scalability | 0 | 5 | 0 | 0 | 5
Security | 0 | 12 | 0 | 0 | 12
PDPA Compliance | 0 | 6 | 0 | 0 | 6
Infrastructure | 0 | 7 | 0 | 0 | 7
Observability | 0 | 5 | 0 | 0 | 5
Accessibility | 0 | 4 | 0 | 0 | 4
Testing & Quality | 0 | 10 | 0 | 0 | 10
Success Metrics | 0 | 0 | 5 | 0 | 5
Out of Scope | 0 | 0 | 0 | 8 | 8
GRAND TOTAL | 120 | 59 | 5 | 8 | 192

## Success KPIs
ClinEdOps — Success Metrics & KPIs
KPI ID | Metric | Baseline | Target | Measurement Method | Source
KPI-001 | Manual data entry / tracking time | Benchmark via user survey | 50% reduction | Pre/post time-motion study | CB
KPI-002 | Data accuracy & completeness | Inconsistent across disciplines | ≥ 90% | Data quality audit on required fields | CB
KPI-003 | Report generation time | ~5 minutes per report | < 1 minute (80% reduction) | Stopwatch timing end-to-end | CB
KPI-004 | Survey completion rate | Baseline via audit | ≥ 30% increase | Compare rates before/after per cohort | CB
KPI-005 | Staff and user satisfaction | Baseline via survey | Measurable improvement | Pre/post satisfaction survey | CB

## Out of Scope
Out of Scope — MVP / POC Phase
Req ID | Item | Rationale | Future Phase
OOS-001 | Student grading / summative assessment | Not part of operational clinical education workflow | N/A
OOS-002 | Financial payment processing | Billing data export in scope; actual payment not | Phase B+
OOS-003 | Patient records / EHR / EMR integration | ClinEdOps is education operations, not clinical | N/A
OOS-004 | Native iOS / Android mobile app | Mobile-responsive web in scope; native app future | Phase D
OOS-005 | Full multi-tenancy rollout | Single-tenant for POC; multi-tenant designed for future | Phase E
OOS-006 | Live video / teleconferencing | Not part of core operations workflow | N/A
OOS-007 | SSO (NUH Azure AD / Singpass) | Email/password for POC; SSO as production enhancement | Phase A
OOS-008 | AI/ML sentiment analysis | ML-ready pipeline designed; ML models post-production | Phase C